## Status
Class Status
Instructions: | For your first assignment you will need to fill out A0_Plan Each week you will fill out the corresponding Ax_Status tab along with your Team Status. Note the gray fields are the field you need to change. All other fields are formulas that will populate back to this page's status. Submit a copy of this file, updated each week.
| Tasking | Percent Complete | Totals |  | Milestones | Done
| Planned/Scheduled | 100% | 42 |  | Basic Certification | 60%
| Story Points Assigned | 100% | 160 |  | Portfolio | 100%
| Completed Tasks | 69.23% | 40 |  | Silver Certification | 60%
[5 empty] | Job Search | 100%
[5 empty] | Professional Development | 40%
| Personal | Velocity | Hrs/Task | Avg Hrs/Task | Team Member | 1 | 2 | 3 | 4 | 5
| Week 01 | 17 | 11.5 | 1.9167 | Week 01 | 0 | 0 | 0 | 0 | 0
| Week 02 | 26 | 14 | 2.3333 | Week 02 | 0 | 0 | 0 | 0 | 0
| Week 03 | 26 | 16 | 2.6667 | Week 03 | 0 | 0 | 0 | 0 | 0
| Week 04 | 30 | 3 | 0.5 | Week 04 | 0 | 0 | 0 | 0 | 0
| Week 05 | 28 | 1.5 | 0.25 | Week 05 | 0 | 0 | 0 | 0 | 0
| Week 06 | 31 | 4.5 | 0.75 | Week 06 | 0 | 0 | 0 | 0 | 0
| Week 07 | 29 | 1.5 | 0.25 | Week 07 | 0 | 0 | 0 | 0 | 0

## Team Status
Team member tasking
Completed Tasks
| Day |  | Angelique | Alayna | Dennis | Team Member 4
Assignment 1
| 1 | 1 | 0_PP1_Planning Schedule | 0_PP1_Planning Schedule | 0_PP1_Planning Schedule
| 1 | 2 | 1_B1_Scheduled Basic Meeting with Career Services | 1_B1_Scheduled Basic Meeting with Career Services | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
| 1 | 3 | 3_B3_Informational Interview Overview | 6_S1_Scheduled Silver Meeting with Career Services | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| 2 | 1 | 4_B4_Interviewing: VMOCK | 29_D1_Ethics in Technology | 2_B2_Create Professional Online Profiles
| 2 | 2 | 2_B2_Create Professional Online Profiles | 2_B2_Create Professional Online Profiles | 3_B3_Informational Interview Overview
| 2 | 3 | 5_B5_Elevator Pitch: 5 Sentences | 3_B3_Informational Interview Overview | 22_J1_Networking List
Velocity
Assignment 2
| 3 | 1 | 6_S1_Scheduled Silver Meeting with Career Services | 32_D4_Design Your Life: Chap 2: Work/Life view/compass | 23_J2_Network Contact List
| 3 | 2 | 7_S2_Completed 100% LinkedIn Profile | 33_D5_Design Your Life: Chap 3: Good Times Journal | 33_D5_Design Your Life: Chap 3: Good Times Journal
| 3 | 3 | 8_S3_Completed 100% BYUI Connect Profile | 34_D6_Design Your Life: Chap 4: Mind Map | 16_P1_Photo
| 4 | 1 | 9_S4_Completed 100% Handshake Profile | 11_S6_Informational Interview 1 | 34_D6_Design Your Life: Chap 4: Mind Map
| 4 | 2 | 10_S5_Resume in Green Zone on VMOCK | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4)
| 4 | 3 | 11_S6_Informational Interview 1 | 7_S2_Completed 100% LinkedIn Profile | 4_B4_Interviewing: VMOCK
Velocity
Assignment 3
| 5 | 1 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass | 35_D7_Design Your Life: Chap 5: Odyssey Plans | 5_B5_Elevator Pitch: 5 Sentences
| 5 | 2 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) | 35_D7_Design Your Life: Chap 5: Odyssey Plans
| 5 | 3 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) | 17_P2_Resume
| 6 | 1 | 33_D5_Design Your Life: Chap 3: Good Times Journal | 12_S7_Informational Interview 2 | 1_B1_Scheduled Basic Meeting with Career Services
| 6 | 2 | 16_P1_Photo | 30_D2_Mental Health & Professional Success | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8)
| 6 | 3 | 17_P2_Resume | 4_B4_Interviewing: VMOCK | 24_J3_Company Dossiers
Velocity
Assignment 4
| 7 | 1 | 18_P3_Cover Letter Template | 24_J3_Company Dossiers | 18_P3_Cover Letter Template
| 7 | 2 | 19_P4_References | 17_P2_Resume
| 7 | 3 | 20_P5_Elevator Pitch/About | 14_S9_Informational Interview 4 | 25_J4_Job Application 1
| 8 | 1 | 21_P6_Projects | 19_P4_References | 19_P4_References
| 8 | 2 | 22_J1_Networking List | 21_P6_Projects | 7_S2_Completed 100% LinkedIn Profile
| 8 | 3 | 23_J2_Network Contact List | 18_P3_Cover Letter Template | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10)
Velocity
Assignment 5
| 9 | 1
| 9 | 2
| 9 | 3
| 10 | 1
| 10 | 2
| 10 | 3
Velocity
Assignment 6
| 11 | 1
| 11 | 2
| 11 | 3
| 12 | 1
| 12 | 2
| 12 | 3
Velocity
Assignment 7
| 13 | 1
| 13 | 2
| 13 | 3
| 14 | 1
| 14 | 2
| 14 | 3
Velocity

## Backlog
BackLog
Count | Ref | Issues | Hidden Colum - create a orginal menu list | Hidden Column - menu list that removes items as selected |  | Hidden status
[5 empty] | 100% | 69.23%
0 | PP1 | Planning Schedule | 0_PP1_Planning Schedule |  | 1 | 1 | Completed
0 | B0 | Basic Certification |  |  |  |  | 60%
1 | B1 | Scheduled Basic Meeting with Career Services | 1_B1_Scheduled Basic Meeting with Career Services |  | 1 | 1
2 | B2 | Create Professional Online Profiles | 2_B2_Create Professional Online Profiles |  | 1 | 1
3 | B3 | Informational Interview Overview | 3_B3_Informational Interview Overview |  | 1 | 1
4 | B4 | Interviewing: VMOCK | 4_B4_Interviewing: VMOCK |  | 1
5 | B5 | Elevator Pitch: 5 Sentences | 5_B5_Elevator Pitch: 5 Sentences |  | 1
0 | S0 | Silver Certification |  |  |  |  | 60%
6 | S1 | Scheduled Silver Meeting with Career Services | 6_S1_Scheduled Silver Meeting with Career Services |  | 1
7 | S2 | Completed 100% LinkedIn Profile | 7_S2_Completed 100% LinkedIn Profile |  | 1
8 | S3 | Completed 100% BYUI Connect Profile | 8_S3_Completed 100% BYUI Connect Profile |  | 1
9 | S4 | Completed 100% Handshake Profile | 9_S4_Completed 100% Handshake Profile |  | 1
10 | S5 | Resume in Green Zone on VMOCK | 10_S5_Resume in Green Zone on VMOCK |  | 1 | 1
11 | S6 | Informational Interview 1 | 11_S6_Informational Interview 1 |  | 1 | 1
12 | S7 | Informational Interview 2 | 12_S7_Informational Interview 2 |  | 1 | 1
13 | S8 | Informational Interview 3 | 13_S8_Informational Interview 3 |  | 1 | 1
14 | S9 | Informational Interview 4 | 14_S9_Informational Interview 4 |  | 1 | 1
15 | S10 | Informational Interview 5 | 15_S10_Informational Interview 5 |  | 1 | 1
0 | P0 | Portfolio Review |  |  |  |  | 100%
16 | P1 | Photo | 16_P1_Photo |  | 1 | 1
17 | P2 | Resume | 17_P2_Resume |  | 1 | 1
18 | P3 | Cover Letter Template | 18_P3_Cover Letter Template |  | 1 | 1
19 | P4 | References | 19_P4_References |  | 1 | 1
20 | P5 | Elevator Pitch/About | 20_P5_Elevator Pitch/About |  | 1 | 1
21 | P6 | Projects | 21_P6_Projects |  | 1 | 1
0 | J0 | Job Search |  |  |  |  | 100%
22 | J1 | Networking List | 22_J1_Networking List |  | 1 | 1
23 | J2 | Network Contact List | 23_J2_Network Contact List |  | 1 | 1
24 | J3 | Company Dossiers | 24_J3_Company Dossiers |  | 1 | 1
25 | J4 | Job Application 1 | 25_J4_Job Application 1 |  | 1 | 1
26 | J5 | Job Application 2 | 26_J5_Job Application 2 |  | 1 | 1
27 | J6 | Job Application 3 | 27_J6_Job Application 3 |  | 1 | 1
28 | J7 | Job Interviewing | 28_J7_Job Interviewing |  | 1 | 1
0 | D0 | Professional Development |  |  |  |  | 40%
29 | D1 | Ethics in Technology | 29_D1_Ethics in Technology |  | 1 | 1
30 | D2 | Mental Health & Professional Success | 30_D2_Mental Health & Professional Success |  | 1 | 1
31 | D3 | Design Your Life: Chap 1: Health, Work, Play, & Love | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love |  | 1 | 1
32 | D4 | Design Your Life: Chap 2: Work/Life view/compass | 32_D4_Design Your Life: Chap 2: Work/Life view/compass |  | 1 | 1
33 | D5 | Design Your Life: Chap 3: Good Times Journal | 33_D5_Design Your Life: Chap 3: Good Times Journal |  | 1
34 | D6 | Design Your Life: Chap 4: Mind Map | 34_D6_Design Your Life: Chap 4: Mind Map |  | 1
35 | D7 | Design Your Life: Chap 5: Odyssey Plans | 35_D7_Design Your Life: Chap 5: Odyssey Plans |  | 1
36 | D8 | The 2-Hour Job Search: Prioritization (Chap 1-4) | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) |  | 1
37 | D9 | The 2-Hour Job Search: Outreach (Chap 5-8) | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) |  | 1
38 | D10 | The 2-Hour Job Search: Execution (Chap 9-10) | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10) |  | 1
0 | A0 | Additional Tasks
39 | A1 | test1 | 39_A1_test1
40 | A2 | test 2 | 40_A2_test 2
41 | A3 | test 3 | 41_A3_test 3
42 | A4 | test 4 | 42_A4_test 4 | 42_A4_test 4

## A0_Plan
|  |  |  | Hidden | Hidden | Hidden | Hidden | Hidden
Assign 0: Planning Schedule | [9 empty] | Story Points Chart
Instructions: | [9 empty] | Complexity | Complexity Description | CS Example Task | Class Example
1 | Read over each of the assignments in the Backlog (found in iLearn course) In the Planning Assignment column, select which task you plan on completing for each day of the semester. | [7 empty] | 1 | 1 Point | Very simple, minimal effort, well understood | Change a button's color in a web app | - Upload a photo for portfolio - Schedule a meeting with Career Services
2 | Examine the Story Point chart to the right. Mouse over and Read the comment in the Story Point column's title (below). | [7 empty] | 2 | 2 Points | Simple task, few moving parts | Add a new field to a database and update UI | - Create Networking List - Write 5-sentence Elevator Pitch
3 | Assign story points to each of the assignments, based on the complexity of the task. | [7 empty] | 3 | 3 Points | Moderate complexity; some research or testing needed | Implement login with form validation | - Complete LinkedIn or Handshake profile - Read and reflect on “Design Your Life: Chap 1–2”
4 | Verify that the Planned Velocity Chart has a even variance and trend. | [7 empty] | 5 | 5 Points | Complex; multiple steps or edge cases | Integrate third-party API (e.g., payment gateway) | - Write a resume or cover letter template - Conduct Informational Interview 1–2
[9 empty] | 8 | 8 Points | Very complex; uncertainty, multiple components | Build a basic real-time chat feature | - Resume in Green Zone on VMOCK - Conduct 4–5 Informational Interviews - Projects section for Portfolio
[9 empty] | 13 | 13 Points | Extremely complex or poorly understood | Refactor large legacy module or migrate backend | - Prepare for and perform Job Interviews - Create full Odyssey Plans (Design Your Life: Chap 5) - Apply to 3 jobs with custom materials
[9 empty] | 21 | 21+ Points | Too large – break this down | “Build entire website” — needs decomposition | - "Complete All Silver Certification Requirements" (too broad; break into subtasks)
Day |  | Planned Assignment | Story Points | Scheduled | SP Complete | Completed | Actual Hours | Linke to Artifacts
1 | 1 | 0_PP1_Planning Schedule | 1 | DAY_1 | 1 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
1 | 2 | 2_B2_Create Professional Online Profiles | 5 | DAY_1 | 1 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
1 | 3 | 1_B1_Scheduled Basic Meeting with Career Services | 1 | DAY_1 | 1 | Done | 0.5 | https://github.com/scottshumway925/prefessionalReadiness
2 | 1 | 3_B3_Informational Interview Overview | 3 | DAY_2 | 1 | Done | 3 | https://github.com/scottshumway925/prefessionalReadiness
2 | 2 | 4_B4_Interviewing: VMOCK | 3 | DAY_2 | 1 | Done | 4 | https://github.com/scottshumway925/prefessionalReadiness
2 | 3 | 5_B5_Elevator Pitch: 5 Sentences | 3 | DAY_2 | 1 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
|  | Assignment 1 Planned Velocity | 16
3 | 1 | 7_S2_Completed 100% LinkedIn Profile | 5 | DAY_3 | 1 | Done | 4 | https://github.com/scottshumway925/prefessionalReadiness
3 | 2 | 11_S6_Informational Interview 1 | 5 | DAY_3 | 1 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
3 | 3 | 12_S7_Informational Interview 2 | 8 | DAY_3 | 1 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
4 | 1 | 9_S4_Completed 100% Handshake Profile | 1 | DAY_4 | 1 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
4 | 2 | 8_S3_Completed 100% BYUI Connect Profile | 3 | DAY_4 | 1 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
4 | 3 | 13_S8_Informational Interview 3 | 5 | DAY_4 | 1 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
|  | Assignment 2 Planned Velocity | 27
5 | 1 | 15_S10_Informational Interview 5 | 5 | DAY_5 | 1 | Done | 3 | https://github.com/scottshumway925/prefessionalReadiness
5 | 2 | 14_S9_Informational Interview 4 | 5 | DAY_5 | 1 | Done | 3 | https://github.com/scottshumway925/prefessionalReadiness
5 | 3 | 6_S1_Scheduled Silver Meeting with Career Services | 3 | DAY_5 | 1 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
6 | 1 | 10_S5_Resume in Green Zone on VMOCK | 3 | DAY_6 | 1 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
6 | 2 | 22_J1_Networking List | 5 | DAY_6 | 1 | Done | 4 | https://github.com/scottshumway925/prefessionalReadiness
6 | 3 | 18_P3_Cover Letter Template | 5 | DAY_6 | 1 | Done | 3 | https://github.com/scottshumway925/prefessionalReadiness
|  | Assignment 3 Planned Velocity | 26
7 | 1 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) | 5 | DAY_7 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
7 | 2 | 30_D2_Mental Health & Professional Success | 3 | DAY_7 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
7 | 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love | 5 | DAY_7 | 1 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
8 | 1 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass | 8 | DAY_8 | 1 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
8 | 2 | 33_D5_Design Your Life: Chap 3: Good Times Journal | 1 | DAY_8 | 1 | Working | 0.5 | https://github.com/scottshumway925/prefessionalReadiness
8 | 3 | 34_D6_Design Your Life: Chap 4: Mind Map | 8 | DAY_8 | 1 | Working | 0.5 | https://github.com/scottshumway925/prefessionalReadiness
|  | Assignment 4 Planned Velocity | 30
9 | 1 | 23_J2_Network Contact List | 3 | DAY_9 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
9 | 2 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) | 8 | DAY_9 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
9 | 3 | 20_P5_Elevator Pitch/About | 3 | DAY_9 | 1 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
10 | 1 | 16_P1_Photo | 5 | DAY_10 | 1 | Done | 0.5 | https://github.com/scottshumway925/prefessionalReadiness
10 | 2 | 25_J4_Job Application 1 | 8 | DAY_10 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
10 | 3 | 41_A3_test 3 | 5 | DAY_10 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
|  | Assignment 5 Planned Velocity | 32
11 | 1 | 21_P6_Projects | 5 | DAY_11 | 1 | Working | 4.5 | https://github.com/scottshumway925/prefessionalReadiness
11 | 2 | 19_P4_References | 5 | DAY_11 | 1 | Done | 0 | https://github.com/scottshumway925/prefessionalReadiness
11 | 3 | 24_J3_Company Dossiers | 5 | DAY_11 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
12 | 1 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10) | 3 | DAY_12 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
12 | 2 | 26_J5_Job Application 2 | 8 | DAY_12 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
12 | 3 | 39_A1_test1 | 5 | DAY_12 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
|  | Assignment 6 Planned Velocity | 31
13 | 1 | 28_J7_Job Interviewing | 5 | DAY_13 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
13 | 2 | 27_J6_Job Application 3 | 8 | DAY_13 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
13 | 3 | 40_A2_test 2 | 5 | DAY_13 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
14 | 1 | 29_D1_Ethics in Technology | 3 | DAY_14 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
14 | 2 | 35_D7_Design Your Life: Chap 5: Odyssey Plans | 3 | DAY_14 | 1 | 0 | 0 | https://github.com/scottshumway925/prefessionalReadiness
14 | 3 | 17_P2_Resume | 5 | DAY_14 | 1
|  | Assignment 7 Planned Velocity | 29
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points are based on complexity of the assignment, not how long it takes. Start with this assignment as a complexity 5. Compare the next assignment you have on the list more or less complex. Continue rake and stacking the assignment’s complexity. (You can go back and change the complexity).
Note on F12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Story points are based on complexity of the assignment, not how long it takes. Start with this assignment as a complexity 5. Compare the next assignment you have on the list more or less complex. Continue rake and stacking the assignment’s complexity. (You can go back and change the complexity).

## A1_Status
|  | Assignment 1: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 1 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 0_PP1_Planning Schedule | 2 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 2_B2_Create Professional Online Profiles | 5 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 1_B1_Scheduled Basic Meeting with Career Services | 1 | Done | 0.5 | https://github.com/scottshumway925/prefessionalReadiness
| Day 2 | Planned |  | Completed? | Actual Hrs
| 1 | 3_B3_Informational Interview Overview | 3 | Done | 3 | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 4_B4_Interviewing: VMOCK | 3 | Done | 4 | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 5_B5_Elevator Pitch: 5 Sentences | 3 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
|  | Total (Velocity) | 17 |  | 11.5
|  | Average | 2.8333 |  | 1.9167
What are you planning on doing?
| Day 3 | Planned |  | See next weeks for status
| 1 | 7_S2_Completed 100% LinkedIn Profile
| 2 | 11_S6_Informational Interview 1
| 3 | 12_S7_Informational Interview 2
| Day 4 | Planned
| 1 | 9_S4_Completed 100% Handshake Profile
| 2 | 8_S3_Completed 100% BYUI Connect Profile
| 3 | 13_S8_Informational Interview 3
Obsticales
Obstacle 1: I struggled to understand what it meant to post artifacts. I’ve settled on the idea of publishing my files to GitHub for easy access, but this could be much more clear. Obstacle 2: Time. I found it hard to make such an immense time commitment to this class, considering I’ve spent well over 6 hours this week for the 1 credit class. Everything flowed really nicely, although it took some time.
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule | Informational interviews aren’t something to fear. They are helpful and should be used as a learning experience.
| Lesson 2 | 2_B2_Create Professional Online Profiles | An online presence is critical. If you don’t advertise yourself well online, then employers will be less likely to look to you as a good candidate. presence is crucial
| Lesson 3 | 1_B1_Scheduled Basic Meeting with Career Services | Conveying who you are in a brief moment is incredibly difficult. In order to show more power, you need to include numbers and show that you truly made a difference. such a small amount of time.
Planned
| Lesson 4 | 3_B3_Informational Interview Overview | Interviewing is tough and requires a lot of practice. I need to learn more technical knowledge instead of just implementation skills, or else I’ll continue to struggle.
| Lesson 5 | 4_B4_Interviewing: VMOCK | Nothing of note for scheduling a meeting.
| Lesson 6 | 5_B5_Elevator Pitch: 5 Sentences | I need to spend time increasing my online marketability through personal projects being pushed to GitHub.
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | I will complete 1 extra assignment each week to ensure that I don’t run into any hiccups with late work.
| Goal 2: | I will reach out to at least 3 professionals each week to get informational interviews set up and completed.
| Goal 3: | I will write my assignments in my planner each day to ensure that I stay ahead of the curve.

## A2_Status
|  | Assignment 2: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 3 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 7_S2_Completed 100% LinkedIn Profile | 5 | Done | 4 | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 11_S6_Informational Interview 1 | 5 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 12_S7_Informational Interview 2 | 5 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
| Day 4 | Planned |  | Completed? | Actual Hrs
| 1 | 9_S4_Completed 100% Handshake Profile | 3 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 8_S3_Completed 100% BYUI Connect Profile | 3 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 13_S8_Informational Interview 3 | 5 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
|  | Total (Velocity) | 26 |  | 14
|  | Average | 4.3333 |  | 2.3333
What are you planning on doing?
| Day 5 | Planned |  | See next weeks for status
| 1 | 15_S10_Informational Interview 5
| 2 | 14_S9_Informational Interview 4
| 3 | 6_S1_Scheduled Silver Meeting with Career Services
| Day 6 | Planned
| 1 | 10_S5_Resume in Green Zone on VMOCK
| 2 | 22_J1_Networking List
| 3 | 18_P3_Cover Letter Template
Obsticales
Obstacle 1: I found that getting things scheduled with professionals is really difficult. In the end, we were able to get things scheduled really nicely and multiple informational interviews planned Obstacle 2: LinkedIn doesn't display the AllStar badge anymore, and the homework asks that I work for the badge. I spent hours looking for the badge, unable to find it.
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule | I learned that LinkedIn has a whole lot of features for me to utilize. I will continue to work through LinkedIn so that I can better my odds of finding recruiters.
| Lesson 2 | 2_B2_Create Professional Online Profiles | My first informational interview taught me that I need to focus heavily on getting some personal projects done.
| Lesson 3 | 1_B1_Scheduled Basic Meeting with Career Services | My second informational interview taught me that I needed to focus on personal projects that directly interest me so that I can better secure a job regarding those things.
Planned
| Lesson 4 | 3_B3_Informational Interview Overview | I learned that through Handshake I have the potential to find a job that I'm directly interested in. It offers so many different options for people who are actively searching for workers.
| Lesson 5 | 4_B4_Interviewing: VMOCK | I actually scheduled an informational interview through iConnect, so I found the use in the social media platform!
| Lesson 6 | 5_B5_Elevator Pitch: 5 Sentences | This interview helped me to reaclize that the peple who I don't necessarily have a connection with are often more than willing to help me out, so reaching out doesn't hurt!
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | I will watch 3 of the videos from Andrej Karpothy so that I can follow up with David Weiss
| Goal 2: | I will reach out to the two contacts that Dennis Bingham offered me so that I can follow up with Dennis.
| Goal 3: | I will follow up with both David and Dennis before the end of the week.

## A3_Status
|  | Assignment 3: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 5 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 15_S10_Informational Interview 5 | 5 | Done | 3 | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 14_S9_Informational Interview 4 | 5 | Done | 3 | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 6_S1_Scheduled Silver Meeting with Career Services | 3 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
| Day 6 | Planned |  | Completed? | Actual Hrs
| 1 | 10_S5_Resume in Green Zone on VMOCK | 3 | Done | 2 | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 22_J1_Networking List | 5 | Done | 4 | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 18_P3_Cover Letter Template | 5 | Done | 3 | https://github.com/scottshumway925/prefessionalReadiness
|  | Total (Velocity) | 26 |  | 16
|  | Average | 4.3333 |  | 2.6667
What are you planning on doing?
| Day 7 | Planned |  | See next weeks for status
| 1 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8)
| 2 | 30_D2_Mental Health & Professional Success
| 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love
| Day 8 | Planned
| 1 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass
| 2 | 33_D5_Design Your Life: Chap 3: Good Times Journal
| 3 | 34_D6_Design Your Life: Chap 4: Mind Map
Obsticales
The Biggest obstacle that I faced this week was time and motivation. I was able to get the work done without too much of a struggle, but I did fight with the urge not to do the work in the first place. I just didn't want to spend the time. I am going to work on my motivation to keep it going well and the work flowing.
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule | I need to get my LinkedIn looking really nice. Employers do check LinkedIn.
| Lesson 2 | 2_B2_Create Professional Online Profiles | I need to learn how to manage multiple AI agents. Doing projects that revolve around these things will better your potential future.
| Lesson 3 | 1_B1_Scheduled Basic Meeting with Career Services | Optimization of LinkedIn is continual. I should always be updating it.
Planned
| Lesson 4 | 3_B3_Informational Interview Overview | There is a lot to getting a resume looking nice. I should continually work to better my resume.
| Lesson 5 | 4_B4_Interviewing: VMOCK | Crafting a list of contacts really isn't all that difficult. You should always grow your contact list!
| Lesson 6 | 5_B5_Elevator Pitch: 5 Sentences | A cover letter is the first impression that I give with my resume, so it needs to be well crafted!
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | Update my resume a little bit each week. This can be as simple as one line or more, but I will read it over and update it.
| Goal 2: | Whenever I finish a project, I will go to LinkedIn and add it to my projects list.
| Goal 3: | I will utilize AI when reviewing my cover letter and resume, integrating some of it's ideas into the paper.

## A4_Status
|  | Assignment 4: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 7 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 37_D9_The 2-Hour Job Search: Outreach (Chap 5-8) | 5 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 30_D2_Mental Health & Professional Success | 3 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 31_D3_Design Your Life: Chap 1: Health, Work, Play, & Love | 5 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
| Day 8 | Planned |  | Completed? | Actual Hrs
| 1 | 32_D4_Design Your Life: Chap 2: Work/Life view/compass | 8 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 33_D5_Design Your Life: Chap 3: Good Times Journal | 1 | Working | 0.5 | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 34_D6_Design Your Life: Chap 4: Mind Map | 8 | Working | 0.5 | https://github.com/scottshumway925/prefessionalReadiness
|  | Total (Velocity) | 30 |  | 3
|  | Average | 5 |  | 0.5
What are you planning on doing?
| Day 9 | Planned |  | See next weeks for status
| 1 | 23_J2_Network Contact List
| 2 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4)
| 3 | 20_P5_Elevator Pitch/About
| Day 10 | Planned
| 1 | 16_P1_Photo
| 2 | 25_J4_Job Application 1
| 3 | 41_A3_test 3
Obsticales
This week I had a lot of classes ask for final project drafts, so time was really tight. I did end up getting most of the portfolio complete, so that's really neat!
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule | Yet to complete.
| Lesson 2 | 2_B2_Create Professional Online Profiles | Yet to complete.
| Lesson 3 | 1_B1_Scheduled Basic Meeting with Career Services | I need to focus on many different aspects of my life, not just the generic "life." I must remember my work, play, health, and love.
Planned
| Lesson 4 | 3_B3_Informational Interview Overview | My workview is driven by my life view. I need to ensure that my lifeview is correct, or else my compass won't be pointing in the correct direction.
| Lesson 5 | 4_B4_Interviewing: VMOCK | Yet to complete.
| Lesson 6 | 5_B5_Elevator Pitch: 5 Sentences | Yet to complete.
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
| Goal 1: | My first goal is to complete this weeks work next week. I bounced around and got some other things done listed in future weeks, so I would like to get back on track this upcoming week
| Goal 2: | I will be spending time refocusing my workview. I don't spend enough time working because of how I view it. I will write some ways that I would like to change my personal view on life and list out how they are changing my actions.
| Goal 3: | I will actively keep track of my daily activities. This is what is holding me up with chapter 3. I keep forgetting to track my time spent.

## A5_Status
|  | Assignment 5: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 9 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 23_J2_Network Contact List | 3 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 36_D8_The 2-Hour Job Search: Prioritization (Chap 1-4) | 8 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 20_P5_Elevator Pitch/About | 3 | Done | 1 | https://github.com/scottshumway925/prefessionalReadiness
| Day 10 | Planned |  | Completed? | Actual Hrs
| 1 | 16_P1_Photo | 1 | Done | 0.5 | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 25_J4_Job Application 1 | 8 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 41_A3_test 3 | 5 |  |  | https://github.com/scottshumway925/prefessionalReadiness
|  | Total (Velocity) | 28 |  | 1.5
|  | Average | 4.6667 |  | 0.25
What are you planning on doing?
| Day 11 | Planned |  | See next weeks for status
| 1 | 21_P6_Projects
| 2 | 19_P4_References
| 3 | 24_J3_Company Dossiers
| Day 12 | Planned
| 1 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10)
| 2 | 26_J5_Job Application 2
| 3 | 39_A1_test1
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 2_B2_Create Professional Online Profiles
| Lesson 3 | 1_B1_Scheduled Basic Meeting with Career Services
Planned
| Lesson 4 | 3_B3_Informational Interview Overview
| Lesson 5 | 4_B4_Interviewing: VMOCK
| Lesson 6 | 5_B5_Elevator Pitch: 5 Sentences
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3:

## A6_Status
|  | Assignment 6: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 11 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 21_P6_Projects | 5 | Working | 4.5 | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 19_P4_References | 5 | Done |  | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 24_J3_Company Dossiers | 5 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| Day 12 | Planned |  | Completed? | Actual Hrs
| 1 | 38_D10_The 2-Hour Job Search: Execution (Chap 9-10) | 3 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 26_J5_Job Application 2 | 8 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 39_A1_test1 | 5 |  |  | https://github.com/scottshumway925/prefessionalReadiness
|  | Total (Velocity) | 31 |  | 4.5
|  | Average | 5.1667 |  | 0.75
What are you planning on doing?
| Day 13 | Planned |  | See next weeks for status
| 1 | 28_J7_Job Interviewing
| 2 | 27_J6_Job Application 3
| 3 | 40_A2_test 2
| Day 14 | Planned
| 1 | 29_D1_Ethics in Technology
| 2 | 35_D7_Design Your Life: Chap 5: Odyssey Plans
| 3 | 17_P2_Resume
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 2_B2_Create Professional Online Profiles
| Lesson 3 | 1_B1_Scheduled Basic Meeting with Career Services
Planned
| Lesson 4 | 3_B3_Informational Interview Overview
| Lesson 5 | 4_B4_Interviewing: VMOCK
| Lesson 6 | 5_B5_Elevator Pitch: 5 Sentences
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3:

## A7_Status
|  | Assignment 7: Status |  |  |  |  | Done
Scrum Status Report – Tracking Professional Progress | [6 empty] | Working
Objective: | [6 empty] | Not Started
Practice accountability and reporting on your professional activities using the Agile Scrum Meeting format. This structured status update will help you track progress, manage assignments efficiently, and develop career readiness skills. Additionally, you will engage with three classmates, tracking their progress and planning to foster collaboration and peer accountability.
Assignment Overview
Since this course is 1 credit, you are expected to complete 3 hours of work per week (semester) or 6 hours per week (block). For every 6 hours of work completed, you will submit a Scrum Status Report: Semester students: Submit a report every two weeks. Block students: Submit a report weekly. To receive full points, you must complete the Class Plan assignment, as you will reference your plan in your status updates.
Part 1: Scrum Status Report
What did you do?
| Day 13 | Planned | Story Points | Completed? | Actual Hrs | Links to artifacts
| 1 | 28_J7_Job Interviewing | 5 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 27_J6_Job Application 3 | 8 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 40_A2_test 2 | 5 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| Day 14 | Planned |  | Completed? | Actual Hrs
| 1 | 29_D1_Ethics in Technology | 3 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 2 | 35_D7_Design Your Life: Chap 5: Odyssey Plans | 3 |  |  | https://github.com/scottshumway925/prefessionalReadiness
| 3 | 17_P2_Resume | 5 | Done | 1.5 | https://github.com/scottshumway925/prefessionalReadiness
|  | Total (Velocity) | 29 |  | 1.5
|  | Average | 4.8333 |  | 0.25
What are you planning on doing?
| Day 15+ | Planned
| 1 | Work on your goals
| 2 | Work on your odyssy plan
| 3 | Find an Internship
| 1 | Plan for Graduate school
| 2 | Find a full time job
3
Obsticales
Part 2: Lessons Learned Reflection
Assignment Overview
For each completed assignment, provide a brief lesson learned: Something new you learned. A mistake and how you corrected it. An “Ah-ha” moment or connection to past experiences. Example Format: Lesson Learned 1: Learned how to use the STAR method to structure resume bullet points. Lesson Learned 2: Found out the importance of reaching out to multiple professionals for interviews instead of waiting on one. Lesson Learned 3: Realized that my LinkedIn profile was missing a strong summary statement.
Planned
| Lesson 1 | 0_PP1_Planning Schedule
| Lesson 2 | 2_B2_Create Professional Online Profiles
| Lesson 3 | 1_B1_Scheduled Basic Meeting with Career Services
Planned
| Lesson 4 | 3_B3_Informational Interview Overview
| Lesson 5 | 4_B4_Interviewing: VMOCK
| Lesson 6 | 5_B5_Elevator Pitch: 5 Sentences
Part 3: SMART Goals for Career Readiness
Based on your progress, create three SMART Goals to start at the end of the semester toward your Career Readiness. SMART Goal Criteria: Specific Measurable Achievable Realistic Time-bound
Example Goals: SMART Goal 1: Complete three informational interviews with software engineers by the end of next month. SMART Goal 2: Earn a LinkedIn Learning certification in data analytics within six weeks. SMART Goal 3: Apply to five internship positions before the end of the semester.
Goal 1:
Goal 2:
Goal 3: